## Sheet1
Bug ID | Module | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG001 | Login | Error message not shown for invalid login attempt | 1. Go to login page 2. Enter invalid credentials 3. Click Login | Proper error message should be displayed | No message displayed | High | High | Open
BUG002 | Registration | Application crashes when email format is invalid | 1. Go to registration page 2. Enter invalid email format 3. Submit | Validation message should be displayed | Application crashes | Critical | High | Open
BUG003 | Job Search | Search returns irrelevant results for specific keywords | 1. Enter keyword 'Designer' 2. Click Search | Only jobs related to 'Designer' should be listed | Unrelated jobs are displayed | Medium | Medium | Open
BUG004 | UI | Alignment issue in the registration form on mobile | 1. Open registration form on a mobile browser | Fields should be aligned properly | Fields are overlapping | Low | Low | Open
BUG005 | Job Apply | Apply button unresponsive on certain job listings | 1. Go to job listing page 2. Click on apply button for specific job | Application process should begin | Nothing happens when button is clicked | High | High | Open